## Action plan
Action Plan Template
Goal: improve customer onboarding satisfaction from 7.1 to 8.0 by June
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/action-plan-template/
# | Action | Owner | Start | Due | Priority
1 | Survey customers about onboarding pain points | J. Patel | 2026-02-02 | 2026-02-13 | High
2 | Rewrite welcome email sequence | M. Lee | 2026-02-09 | 2026-02-20 | Medium
3 | Record three how-to videos | S. Gomez | 2026-02-16 | 2026-03-06 | Medium
4 | Review results and decide next steps | Team lead | 2026-03-09 | 2026-03-10 | High