## Instructions
Action Plan Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/action-plan-template/
Step | How to use this template
1 | Write the goal at the top in one measurable sentence.
2 | List the actions needed to reach it, starting with a verb.
3 | Assign one owner, a start date and a due date to each action.
4 | Note resources and how you will know each action is done.
5 | Set priority and review status weekly until the goal is met.
Tip | Getting the most from it
1 | Keep actions small enough to finish in a few weeks.
2 | One owner per action, even if many help.
3 | Review the plan in a regular meeting.
4 | Close or replace actions that no longer help the goal.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Action Plan Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/action-plan-template/
Total rows with data
Owner | Count | Share
J. Patel
M. Lee
S. Gomez
Team lead
Priority | Count | Share
High
Medium
Low
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Action plan
Action Plan Template
Goal: improve customer onboarding satisfaction from 7.1 to 8.0 by June
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/action-plan-template/
# | Action | Owner | Start | Due | Resources needed | Success measure | Priority | Status
1 | Survey customers about onboarding pain points | J. Patel | 2026-02-02 | 2026-02-13 | Survey tool | 100 responses | High | In progress
2 | Rewrite welcome email sequence | M. Lee | 2026-02-09 | 2026-02-20 | Copywriter (3 days) | Open rate above 45% | Medium | Not started
3 | Record three how-to videos | S. Gomez | 2026-02-16 | 2026-03-06 | Video tool | Videos live in help centre | Medium | Not started
4 | Review results and decide next steps | Team lead | 2026-03-09 | 2026-03-10 | 1-hour meeting | Decision recorded | High | Not started

## Revision history
Action Plan Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/action-plan-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template