## Agile plan
Agile Project Plan Template
Plan epics by Sprint; adapt every Sprint Review
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/agile-project-plan-template/
Sprint | Dates | Sprint goal | Epics / features | Planned points | Release? | Status
Sprint 1 | 2 – 13 Mar | Users can log in securely | Login, password reset | 26 | No | Done
Sprint 2 | 16 – 27 Mar | Users can view invoices | Invoices list, PDF download | 28 | No | In progress
Sprint 3 | 30 Mar – 10 Apr | Admins can manage users | User admin, exports | 30 | Yes (R1) | Not started
Sprint 4 | 13 – 24 Apr | Help content in-app | Help centre | 28 | No | Not started

## Charter
Agile Project Plan Template
A lightweight agile project charter
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/agile-project-plan-template/
Item | Details
Product vision
Goals / success measures
Product Owner
Scrum Master
Developers
Stakeholders
Sprint length | 2 weeks
Ceremonies | Sprint Planning (Mon), Daily Scrum (09:30), Review and Retrospective (last Fri)
Definition of Done
Key risks
Budget / constraints