## Change log
Change Request Template
Log every change request and its decision
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
CR # | Date raised | Raised by | Change description | Reason | Impact: scope | Impact: time (days) | Impact: cost ($) | Priority | Decision | Approved by | Decision date
CR-001 | 2026-02-10 | Sales lead | Add export to CSV on invoices page | Customer requests | Minor addition | 3 | 2400 | Medium | Approved | Sponsor | 2026-02-12
CR-002 | 2026-02-18 | Security | Add multi-factor login | Security policy | New feature | 10 | 9000 | High | Approved | Steering group | 2026-02-24
CR-003 | 2026-03-01 | Marketing | Change brand colours | Rebrand | Design rework | 5 | 3500 | Low | Deferred | Sponsor | 2026-03-04

## Change request form
Change Request Template
Use one form per change
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
Field | Details
Change request number
Requested by / date
Description of change
Reason / benefit
Options considered
Impact on scope
Impact on schedule
Impact on cost
Impact on quality and risk
Recommendation
Decision and conditions
Approved by / date