## Communication plan
Communication Plan Template
Who needs what, when, how and from whom
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/communication-plan-template/
Communication | Audience | Purpose / content | Channel | Frequency | Owner | Format | Feedback route
Status report | Sponsor, steering group | Progress, RAG status, risks, decisions needed | Email + dashboard | Weekly | Project manager | 1-page report | Reply or steering meeting
Steering committee | Steering group | Decisions, escalations, budget | Meeting | Monthly | Sponsor | Slides | Minutes and actions
Team stand-up | Project team | Today's work and blockers | Video call | Daily | Team lead | 15-minute meeting | In the meeting
Stakeholder newsletter | Wider organisation | What's changing and when | Intranet | Monthly | Comms lead | Article | Comments
Go-live notice | Customers | New features and support | Email | Once | Marketing | Email | Support inbox