## Instructions
Critical Path Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/critical-path-template/
Step | How to use this template
1 | List activities, durations (days) and predecessors.
2 | Forward pass: ES = the largest EF of all predecessors (0 for the first); EF = ES + duration.
3 | Backward pass: LF of the last activity = its EF; LS = LF − duration; work backwards using the smallest LS of successors.
4 | Total float = LS − ES; activities with zero float are critical.
5 | Focus monitoring on the critical path; see forward and backward pass.
Tip | Getting the most from it
1 | Re-run the calculation when durations change.
2 | Watch near-critical paths with little float.
3 | Use schedule compression only on critical activities.
4 | Software calculates CPM automatically for large projects.
Tabs: Revision history records changes to this file.

## CPM
Critical Path Template
Enter ES from the forward pass and LS from the backward pass; float and critical flag calculate
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/critical-path-template/
Activity | Description | Duration | Predecessors | ES | EF | LS | LF | Total float | Critical?
A | Requirements | 4 |  | 0 |  | 0
B | Design | 3 | A | 4 |  | 4
C | Procure hardware | 2 | A | 4 |  | 8
D | Build | 5 | B | 7 |  | 7
E | Install hardware | 2 | C | 6 |  | 10
F | Test and launch | 2 | D, E | 12 |  | 12

## Revision history
Critical Path Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/critical-path-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template