## Checklist
Event Planning Template
Event: Customer summit · Date: 25 May 2026
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Weeks before | Task | Owner | Due date | Status | Notes
12 | Set goals, audience and budget | Event lead | 2026-03-02 | Done
10 | Book venue | Event lead | 2026-03-16 | In progress | Two options
8 | Confirm speakers | Programme lead | 2026-03-30 | Not started
6 | Open registration | Marketing | 2026-04-13 | Not started
4 | Order catering and AV | Ops | 2026-04-27 | Not started
2 | Send joining instructions | Marketing | 2026-05-11 | Not started
0 | Run event and collect feedback | All | 2026-05-25 | Not started

## Budget
Event Planning Template
Track estimated versus actual spend
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Item | Category | Estimated ($) | Actual ($) | Variance ($) | Vendor | Paid?
Venue hire | Venue | 6000 | 6000 |  | City Hall | Yes
Catering | Food | 4500 |  |  |  | No
AV and streaming | Tech | 3000 |  |  |  | No
Speaker travel | People | 2000 |  |  |  | No
Total