## Instructions
Kanban Board Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/kanban-board-template/
Step | How to use this template
1 | Rename the columns to match your workflow and set a WIP limit for each.
2 | Add work items as cards in the Backlog column.
3 | Pull cards to the right only when there is capacity under the WIP limit.
4 | Record start and finish dates on the Cards tab to measure cycle time.
5 | Review the board daily and improve the process regularly.
Tip | Getting the most from it
1 | Lower WIP limits until work flows smoothly.
2 | Make blocked work visible.
3 | Use classes of service for urgent work.
4 | See our Kanban boards guide for more.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Kanban Board Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/kanban-board-template/
Total rows with data
Owner | Count | Share
Ana
Ben
Chen
Dana

## Board
Kanban Board Template
Move cards right; respect WIP limits
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/kanban-board-template/
Backlog | To do (WIP 5) | In progress (WIP 3) | Review (WIP 2) | Done
Update pricing page | Write case study | Redesign onboarding email | Q1 report | Customer survey
Partner webinar | Fix broken links | SEO audit |  | New logo files
Translate help centre | Plan April newsletter

## Cards
Kanban Board Template
Track start and finish dates to measure cycle time
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/kanban-board-template/
Card | Owner | Class of service | Column | Started | Finished | Cycle time (days) | Blocked?
Redesign onboarding email | Ana | Standard | In progress | 2026-03-02 |  |  | No
SEO audit | Ben | Standard | In progress | 2026-03-04 |  |  | Yes
Q1 report | Chen | Fixed date | Review | 2026-02-26 |  |  | No
Customer survey | Dana | Standard | Done | 2026-02-20 | 2026-02-27 |  | No

## Revision history
Kanban Board Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/kanban-board-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template