## Lessons learned
Lessons Learned Template
Capture lessons during the project, not only at the end
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/lessons-learned-template/
# | Phase / area | What happened | Went well or needs improvement? | Root cause | Impact | Recommendation | Owner | Action status
1 | Planning | Requirements signed off two weeks early | Went well | Product owner available daily | Medium | Secure product owner time in the charter | PMO | Done
2 | Build | Test environment unavailable for 5 days | Needs improvement | No environment booking process | High | Book environments at planning; add health checks | Ops lead | In progress
3 | Communication | Stakeholders unclear on go-live date | Needs improvement | Date changed without update | Medium | Publish dates in a single dashboard | PM | Not started