## Lessons learned
Lessons Learned Template
Capture lessons during the project, not only at the end
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/lessons-learned-template/
Phase / area | What happened | Went well or needs improvement? | Recommendation | Owner
Planning | Requirements signed off two weeks early | Went well | Secure product owner time in the charter | PMO
Build | Test environment unavailable for 5 days | Needs improvement | Book environments at planning; add health checks | Ops lead
Communication | Stakeholders unclear on go-live date | Needs improvement | Publish dates in a single dashboard | PM