## Instructions
Lessons Learned Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/lessons-learned-template/
Step | How to use this template
1 | Collect lessons throughout the project, for example after each phase or sprint.
2 | Record what happened and whether it went well or needs improvement.
3 | Find the root cause; a 5 whys template helps.
4 | Turn each lesson into a recommendation with an owner.
5 | Share lessons with the PMO and check actions are completed.
Tip | Getting the most from it
1 | Focus on processes, not blame.
2 | Record successes as well as problems.
3 | Make recommendations specific and actionable.
4 | Review past lessons when starting a new project.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Lessons Learned Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/lessons-learned-template/
Total rows with data
Owner | Count | Share
Ops lead
PM
PMO
Action status | Count | Share
Not started
In progress
Done

## Lessons learned
Lessons Learned Template
Capture lessons during the project, not only at the end
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/lessons-learned-template/
# | Phase / area | What happened | Went well or needs improvement? | Root cause | Impact | Recommendation | Owner | Action status
1 | Planning | Requirements signed off two weeks early | Went well | Product owner available daily | Medium | Secure product owner time in the charter | PMO | Done
2 | Build | Test environment unavailable for 5 days | Needs improvement | No environment booking process | High | Book environments at planning; add health checks | Ops lead | In progress
3 | Communication | Stakeholders unclear on go-live date | Needs improvement | Date changed without update | Medium | Publish dates in a single dashboard | PM | Not started

## Revision history
Lessons Learned Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/lessons-learned-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template