## Instructions
Product Backlog Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-backlog-template/
Step | How to use this template
1 | Add every known item: stories, bugs, spikes and technical debt.
2 | Order the list by value, risk and dependencies; the Product Owner decides the order.
3 | Refine top items with the team and estimate them; see backlog refinement.
4 | Mark items Ready when they meet your readiness checklist.
5 | Pull ready items into Sprint Planning.
Tip | Getting the most from it
1 | Keep only the top items detailed.
2 | Remove items that no longer add value.
3 | Make the Product Goal visible above the backlog.
4 | Use user stories for clarity.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Product Backlog Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-backlog-template/
Total rows with data
Type | Count | Share
Story
Bug
Spike
Tech debt
Epic
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Product Backlog
Product Backlog Template
Ordered by the Product Owner: top items are refined and ready
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-backlog-template/
Order | ID | Item / user story | Type | Value (1-10) | Estimate (points) | Ready? | Sprint | Status
1 | PB-101 | As a customer, I can reset my password by email | Story | 9 | 5 | Yes | 14 | In progress
2 | PB-102 | As a customer, I can download invoices as PDF | Story | 8 | 3 | Yes | 14 | Not started
3 | PB-110 | Fix timeout on invoice search | Bug | 7 | 2 | Yes |  | Not started
4 | PB-115 | Spike: evaluate search library | Spike | 6 | 3 | Yes |  | Not started
5 | PB-120 | As an admin, I can export user lists | Story | 5 | 8 | No |  | Not started
6 | PB-130 | Upgrade logging framework | Tech debt | 4 | 5 | No |  | Not started

## Revision history
Product Backlog Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-backlog-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template