## Roadmap
Product Roadmap Template
Now, next, later: shade the quarters each initiative runs
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-roadmap-template/
Theme | Initiative | Goal / outcome | Q1 | Q2 | Q3 | Q4 | Owner | Confidence | Status
Self-service | Customer portal | Cut support calls 30% | ■ | ■ |  |  | Product | High | In progress
Self-service | In-app help centre | Raise CSAT to 8.5 |  | ■ | ■ |  | Product | Medium | Not started
Growth | Partner integrations | 20 new partners |  |  | ■ | ■ | Partnerships | Medium | Not started
Platform | Move to cloud hosting | 99.9% uptime | ■ | ■ | ■ |  | Engineering | High | In progress
Platform | Single sign-on | Enterprise readiness |  |  |  | ■ | Engineering | Low | Not started