## Project charter
Project Charter Template
Complete each section and get the sponsor's sign-off
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-charter-template/
Section | Guidance | Your content
Project name | Short, memorable name used in all communications. | Customer Portal
Purpose / business case | Why the project is needed and the benefits expected. | Reduce account-related support calls by letting customers self-serve.
Objectives (SMART) | Measurable outcomes with dates. | Cut account-related calls by 30% within 6 months of launch.
In scope | What the project will deliver. | Account view, invoices, password reset.
Out of scope | What it will not deliver. | Mobile app; payments.
Key deliverables | Main outputs. | Portal release 1; training guide; support runbook.
Milestones | Major dates. | Design sign-off 15 Feb; Go-live 31 Mar.
Budget | Approved budget or range. | $150,000
Key risks | Top risks known at the start. | Billing system integration delays.
Assumptions and constraints | What you assume to be true and the limits you must work within. | Billing API available by 1 Feb.
Stakeholders | Key people and groups affected. | Customer service, IT, Finance, customers.
Sponsor | Accountable executive. | Head of Customer Service
Project manager and authority | Who leads and what they can decide. | A. Rossi; can approve changes up to $5,000.
Approval | Name, signature and date.