## Instructions
Project Cost Estimate Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-cost-estimate-template/
Step | How to use this template
1 | List tasks or work packages from your WBS.
2 | For each, enter the resource, unit, quantity and rate.
3 | Choose an estimating method for each line.
4 | Review the subtotal, contingency and total.
5 | Agree the estimate and use it as your cost baseline.
Tip | Getting the most from it
1 | Estimate with the people doing the work.
2 | Record assumptions for each line.
3 | Use three-point estimates for uncertain items.
4 | See cost estimation for methods.
Tabs: Revision history records changes to this file.

## Cost estimate
Project Cost Estimate Template
Quantity x rate; contingency and total calculate automatically
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-cost-estimate-template/
WBS / task | Description | Resource | Unit | Quantity | Rate ($) | Cost ($) | Estimate type | Notes
1.1 | Project management | Project manager | day | 20 | 650 |  | Bottom-up
1.2 | Requirements | Business analyst | day | 10 | 550 |  | Bottom-up
1.3 | Development | Developer | day | 60 | 600 |  | Analogous | Based on last portal project
1.4 | Cloud hosting (year 1) | Hosting | month | 12 | 400 |  | Vendor quote
1.5 | Testing | QA engineer | day | 15 | 500 |  | Parametric | 25% of dev effort
Subtotal
| Contingency (10%) | [6 empty] | For identified risks
Total estimate

## Revision history
Project Cost Estimate Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-cost-estimate-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template