## Deliverables
Project Deliverables Template
Agree acceptance criteria before work starts
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-deliverables-template/
ID | Deliverable | Description | Type | Owner | Due date | Acceptance criteria | Approver | Status
D1 | Requirements specification | Signed-off business and functional requirements | Internal | BA | 2026-02-13 | Approved by product owner and sponsor | Sponsor | Done
D2 | Design pack | UX designs and technical architecture | Internal | Design lead | 2026-03-06 | Reviewed by architecture board | CTO | In progress
D3 | Portal release 1 | Working portal in production | External | Tech lead | 2026-04-30 | All P1 tests pass; UAT signed | Sponsor | Not started
D4 | Training guide | Guide for support staff | External | Trainer | 2026-04-24 | Reviewed by support manager | Support manager | Not started