## Schedule
Project Schedule Template
End dates calculate from start date and duration (calendar days)
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-schedule-template/
ID | Task | Owner | Start | Duration (days) | End | Predecessor | % complete | Milestone? | Status
1 | Kick-off meeting | PM | 2026-03-02 | 1 |  |  | 100 | Yes | Done
2 | Gather requirements | BA | 2026-03-03 | 5 |  | 1 | 60 |  | In progress
3 | Design | Designer | 2026-03-10 | 8 |  | 2 | 0 |  | Not started
4 | Build | Developers | 2026-03-20 | 15 |  | 3 | 0 |  | Not started
5 | Test | QA | 2026-04-10 | 6 |  | 4 | 0 |  | Not started
6 | Launch | PM | 2026-04-20 | 1 |  | 5 | 0 | Yes | Not started