## Release plan
Agile Release Plan Template
Forecast capacity assumes a velocity of 30 points per Sprint: change it to yours
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/release-plan-template/
Release | Target date | Sprint | Feature / epic | Story points
R1 | 2026-04-30 | S1 | Password reset | 13
R1 | 2026-04-30 | S2 | Invoice downloads | 18
R1 | 2026-04-30 | S3 | Admin exports | 21
R2 | 2026-06-30 | S4 | Help centre | 25
R2 | 2026-06-30 | S5 | Notifications | 30