## Instructions
Agile Release Plan Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/release-plan-template/
Step | How to use this template
1 | List the features or epics for each release with estimates.
2 | Set your average velocity; capacity accumulates by Sprint.
3 | Check cumulative points against forecast capacity: 'No' means the scope will not fit.
4 | Adjust scope or dates and agree the plan with stakeholders.
5 | Update after every Sprint Review.
Tip | Getting the most from it
1 | Use a range of velocities for honest forecasts.
2 | Put the most valuable features first.
3 | For SAFe, use it as a simple PI planning worksheet.
4 | Keep release goals visible.
Tabs: Revision history records changes to this file.

## Release plan
Agile Release Plan Template
Forecast capacity assumes a velocity of 30 points per Sprint: change it to yours
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/release-plan-template/
Release | Target date | Sprint | Feature / epic | Story points | Cumulative points | Forecast capacity | On track? | Risks / notes
R1 | 2026-04-30 | S1 | Password reset | 13
R1 | 2026-04-30 | S2 | Invoice downloads | 18
R1 | 2026-04-30 | S3 | Admin exports | 21 |  |  |  | Depends on API
R2 | 2026-06-30 | S4 | Help centre | 25
R2 | 2026-06-30 | S5 | Notifications | 30 |  |  |  | New team member

## Revision history
Agile Release Plan Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/release-plan-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template