## Risk register
Risk Register Template
Score = probability x impact; 15-25 high, 8-14 medium, 1-7 low
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/risk-register-template/
ID | Risk (cause → event → effect) | Probability (1-5) | Impact (1-5) | Score | Owner | Status
R1 | Supplier capacity is limited, so hardware may arrive late, delaying installation | 3 | 4 |  | Procurement | In progress
R2 | Key developer may leave, causing loss of knowledge and delay | 2 | 4 |  | Tech lead | In progress
R3 | New regulation may require extra data controls, increasing scope | 2 | 3 |  | PM | Not started
R4 | Exchange-rate changes may raise licence costs | 3 | 2 |  | Finance | Done