## 5 whys
Root Cause Analysis (5 Whys) Template
Keep asking why until you reach a cause you can fix
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Step | Question | Answer
Problem | What happened, where, when and how much? | Release 2.3 was delayed by 9 days
Why 1 | Why did it happen? | Testing started late
Why 2 | Why? | The test environment was not ready
Why 3 | Why? | Environment requests were raised two days before testing
Why 4 | Why? | Environment needs are not part of sprint planning
Why 5 | Why? | There is no checklist for release prerequisites
Root cause | Summarise the root cause | No release prerequisites checklist in planning

## Corrective actions
Root Cause Analysis (5 Whys) Template
Fix the root cause, not just the symptom
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Action | Type | Owner | Due date | How we will verify it worked | Status
Add environment readiness to sprint planning checklist | Prevent | Scrum Master | 2026-03-20 | Next 3 releases start testing on time | Not started
Book environments at release planning | Prevent | Ops lead | 2026-03-27 | Bookings logged 2 weeks ahead | Not started