## Instructions
Root Cause Analysis (5 Whys) Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Step | How to use this template
1 | Write a specific, factual problem statement.
2 | Ask 'why?' and record the answer; repeat about five times.
3 | Stop when you reach a cause you can act on.
4 | Agree corrective actions with owners and dates.
5 | Verify that the actions prevented recurrence.
Tip | Getting the most from it
1 | Base each answer on evidence.
2 | There may be several root causes: branch the analysis.
3 | Focus on processes, not people.
4 | For complex problems, use a fishbone diagram.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Root Cause Analysis (5 Whys) Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Total rows with data
Type | Count | Share
Contain
Correct
Prevent
Owner | Count | Share
Ops lead
Scrum Master
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## 5 whys
Root Cause Analysis (5 Whys) Template
Keep asking why until you reach a cause you can fix
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Step | Question | Answer
Problem | What happened, where, when and how much? | Release 2.3 was delayed by 9 days
Why 1 | Why did it happen? | Testing started late
Why 2 | Why? | The test environment was not ready
Why 3 | Why? | Environment requests were raised two days before testing
Why 4 | Why? | Environment needs are not part of sprint planning
Why 5 | Why? | There is no checklist for release prerequisites
Root cause | Summarise the root cause | No release prerequisites checklist in planning

## Corrective actions
Root Cause Analysis (5 Whys) Template
Fix the root cause, not just the symptom
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Action | Type | Owner | Due date | How we will verify it worked | Status
Add environment readiness to sprint planning checklist | Prevent | Scrum Master | 2026-03-20 | Next 3 releases start testing on time | Not started
Book environments at release planning | Prevent | Ops lead | 2026-03-27 | Bookings logged 2 weeks ahead | Not started

## Revision history
Root Cause Analysis (5 Whys) Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/root-cause-analysis-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template