## Sprint plan
Sprint Planning Template
Sprint Goal: customers can manage their account without calling support
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Backlog item | User story / description | Story points | Owner | Tasks | Acceptance criteria | Status
PB-101 | As a customer, I can reset my password by email | 5 | Ana | API endpoint; email template; tests | Reset link expires after 1 hour | Not started
PB-102 | As a customer, I can download invoices as PDF | 3 | Ben | PDF service; download button | PDF matches invoice data | Not started
PB-103 | As support, I can see a customer's last login | 2 | Chen | Admin view field; audit log | Shows date and time in local zone | Not started
PB-104 | Spike: evaluate search library | 3 | Dana | Prototype two libraries | Recommendation documented | Not started
Total

## Capacity
Sprint Planning Template
Check capacity before committing to the Sprint Backlog
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Team member | Available days | Focus factor | Capacity (days) | Notes
Ana | 9 | 0.8 |  | 1 day leave
Ben | 10 | 0.8
Chen | 8 | 0.7 |  | Support rota
Dana | 10 | 0.8
Team total