## Sprint plan
Sprint Planning Template
Sprint Goal: customers can manage their account without calling support
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Backlog item | User story / description | Owner | Tasks | Status
PB-101 | As a customer, I can reset my password by email | Ana | API endpoint; email template; tests | Not started
PB-102 | As a customer, I can download invoices as PDF | Ben | PDF service; download button | Not started
PB-103 | As support, I can see a customer's last login | Chen | Admin view field; audit log | Not started
PB-104 | Spike: evaluate search library | Dana | Prototype two libraries | Not started
Total