## Instructions
Sprint Planning Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Step | How to use this template
1 | Fill in the Capacity tab: available days per person and a realistic focus factor.
2 | Agree the Sprint Goal with the Product Owner.
3 | Select the top Product Backlog items that support the goal and fit the team's capacity and recent velocity.
4 | Break each item into tasks and confirm acceptance criteria.
5 | Use the Status column during the Sprint and review it at the Sprint Review.
Tip | Getting the most from it
1 | Plan to about 80% of capacity to leave room for the unexpected.
2 | One clear Sprint Goal beats a list of unrelated items.
3 | Bring refined items to planning; see backlog refinement.
4 | Time-box planning to 8 hours for a one-month Sprint.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Sprint Planning Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Total rows with data
Owner | Count | Share
Ana
Ben
Chen
Dana
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Sprint plan
Sprint Planning Template
Sprint Goal: customers can manage their account without calling support
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Backlog item | User story / description | Story points | Owner | Tasks | Acceptance criteria | Status
PB-101 | As a customer, I can reset my password by email | 5 | Ana | API endpoint; email template; tests | Reset link expires after 1 hour | Not started
PB-102 | As a customer, I can download invoices as PDF | 3 | Ben | PDF service; download button | PDF matches invoice data | Not started
PB-103 | As support, I can see a customer's last login | 2 | Chen | Admin view field; audit log | Shows date and time in local zone | Not started
PB-104 | Spike: evaluate search library | 3 | Dana | Prototype two libraries | Recommendation documented | Not started
Total

## Capacity
Sprint Planning Template
Check capacity before committing to the Sprint Backlog
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Team member | Available days | Focus factor | Capacity (days) | Notes
Ana | 9 | 0.8 |  | 1 day leave
Ben | 10 | 0.8
Chen | 8 | 0.7 |  | Support rota
Dana | 10 | 0.8
Team total

## Revision history
Sprint Planning Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-planning-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template