## Retrospective
Sprint Retrospective Template
Sprint 14 · 3-16 March
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Category | Observation | Votes | Discussion notes
Went well | Daily Scrums finished on time | 3
Went well | Pairing on the payments story | 4
To improve | Stories arrived in planning without acceptance criteria | 6 | Refine earlier
To improve | Build pipeline failed twice | 5
Ideas | Try a mid-Sprint refinement session | 4
Shout-outs | Thanks to Chen for fixing the test data | 2

## Action items
Sprint Retrospective Template
Pick one to three improvements; review them next retrospective
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Action | Owner | Due | Success measure | Status
Hold a 1-hour refinement session mid-Sprint | Product Owner | 2026-03-25 | All top-10 items have acceptance criteria | Not started
Add pipeline health alert to team channel | Ben | 2026-03-20 | Failures noticed within 10 minutes | Not started