## WBS
Work Breakdown Structure (WBS) Template
Decompose deliverables into work packages; totals roll up automatically
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-breakdown-structure-template/
WBS code | Level | Deliverable / work package | Description | Owner | Effort (days) | Cost ($) | Status
1 | 1 | Customer portal | The complete project | Project manager |  |  | In progress
1.1 | 2 | Project management | Planning, reporting, governance | Project manager | 10 | 8000 | In progress
1.2 | 2 | Requirements | Workshops and signed-off requirements | Business analyst | 8 | 6400 | Done
1.3 | 2 | Design | UX and technical design | Design lead | 12 | 9600 | In progress
1.4 | 2 | Build | Front end, back end and integrations | Tech lead | 40 | 32000 | Not started
1.5 | 2 | Testing | System and user acceptance testing | QA lead | 15 | 12000 | Not started
1.6 | 2 | Training | Guides and sessions for support staff | Trainer | 5 | 4000 | Not started
1.7 | 2 | Deployment | Release and hypercare | Ops lead | 6 | 4800 | Not started