## Instructions
Work Breakdown Structure (WBS) Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-breakdown-structure-template/
Step | How to use this template
1 | Write the project's final deliverable as level 1.
2 | Break it into major deliverables or phases at level 2, then into work packages at level 3.
3 | Give each element a unique WBS code, a short description and a single owner.
4 | Estimate effort and cost for each work package; the top row totals them.
5 | Check the 100% rule: the children of each element add up to all of its work, and nothing more.
6 | Use the work packages to build your schedule and budget.
Tip | Getting the most from it
1 | Name elements with nouns (deliverables), not verbs.
2 | Stop decomposing when a work package can be estimated and assigned.
3 | Keep a WBS dictionary for detail.
4 | Do not include work that is out of scope.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Work Breakdown Structure (WBS) Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-breakdown-structure-template/
Total rows with data
Owner | Count | Share
Business analyst
Design lead
Ops lead
Project manager
QA lead
Tech lead
Trainer
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## WBS
Work Breakdown Structure (WBS) Template
Decompose deliverables into work packages; totals roll up automatically
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-breakdown-structure-template/
WBS code | Level | Deliverable / work package | Description | Owner | Effort (days) | Cost ($) | Status
1 | 1 | Customer portal | The complete project | Project manager |  |  | In progress
1.1 | 2 | Project management | Planning, reporting, governance | Project manager | 10 | 8000 | In progress
1.2 | 2 | Requirements | Workshops and signed-off requirements | Business analyst | 8 | 6400 | Done
1.3 | 2 | Design | UX and technical design | Design lead | 12 | 9600 | In progress
1.4 | 2 | Build | Front end, back end and integrations | Tech lead | 40 | 32000 | Not started
1.5 | 2 | Testing | System and user acceptance testing | QA lead | 15 | 12000 | Not started
1.6 | 2 | Training | Guides and sessions for support staff | Trainer | 5 | 4000 | Not started
1.7 | 2 | Deployment | Release and hypercare | Ops lead | 6 | 4800 | Not started

## Revision history
Work Breakdown Structure (WBS) Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-breakdown-structure-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-09 |  | First version created from the template