## Work package
Work Package Template
One sheet per work package
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-package-template/
Field | Details
WBS code | 1.4.2
Work package name | Customer login and password reset
Owner | Tech lead
Description / scope | Build login, logout and password reset using single sign-on.
Deliverables | Working feature in test environment; unit tests; release notes.
Tasks | Design screens; build API; integrate SSO; write tests.
Effort estimate (days) | 12
Cost estimate ($) | 9,600
Start / finish | 2 Mar 2026 / 17 Mar 2026
Dependencies | SSO service (IT security project)
Acceptance criteria | All login test cases pass; security review approved.
Risks | SSO delay
Approved by / date